## ISQA 4110
| G6 Maverick Analyzers | [7 empty] | ► Watch How to Make a Gantt Chart in Excel
| ISQA 4110 Gantt Chart |  | Project Start: | 2023-08-07
| Michael Mulvey, Evelyn Espinoza-Macias, |  | Today: | 2023-12-04 13:33
| Miguel Rocha, Natalie Moore |  | Display Week: | 1 |  |  |  | 2023-08-07 | [6 empty] | 2023-08-14 | [6 empty] | 2023-08-21 | [6 empty] | 2023-08-28 | [6 empty] | 2023-09-04 | [6 empty] | 2023-09-11 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25 | [6 empty] | 2023-10-02 | [6 empty] | 2023-10-09 | [6 empty] | 2023-10-16 | [6 empty] | 2023-10-23 | [6 empty] | 2023-10-30 | [6 empty] | 2023-11-06 | [6 empty] | 2023-11-13 | [6 empty] | 2023-11-20 | [6 empty] | 2023-11-27 | [6 empty] | 2023-12-04
|  |  |  | *LEAVE AS WEEK 1* |  |  |  | 2023-08-07 | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | 2023-08-13 | 2023-08-14 | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-18 | 2023-08-19 | 2023-08-20 | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | 2023-08-26 | 2023-08-27 | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-09-01 | 2023-09-02 | 2023-09-03 | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-08 | 2023-09-09 | 2023-09-10 | 2023-09-11 | 2023-09-12 | 2023-09-13 | 2023-09-14 | 2023-09-15 | 2023-09-16 | 2023-09-17 | 2023-09-18 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
ID | TASK | ASSIGNED TO | PROGRESS | START | END | Estimated Hours | ACTUAL HOURS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
[6 empty] | 73.5 | 78.8
Milestone 1
1 | Create and Revise Client Documents | All | 100% | 2023-08-07 | 2023-08-20 | 6 | 6 | 2023-08-21 2023-08-21 M: 100%
2 | Meeting with GA | All | 100% | 2023-09-05 | 2023-09-05 | 0.25 | 0.25 | 2023-09-04 2023-09-06 W: 100%
3 | Create and Revise Roles and Responsibilities | All | 100% | 2023-08-31 | 2023-09-07 | 1 | 1 | 2023-09-04 2023-09-08 F: 100%
4 | Create and Revise Communications Management Plan | Miguel | 100% | 2023-08-31 | 2023-09-07 | 0.5 | 1 | 2023-09-04 2023-09-08 F: 100%
5 | Create and Revise Team Member Status Report | Miguel | 100% | 2023-08-31 | 2023-09-07 | 2 | 4 | 2023-09-04 2023-09-08 F: 100%
6 | Create and Revise System Service Request | All | 100% | 2023-09-07 | 2023-09-10 | 3 | 4 | 2023-09-11 2023-09-11 M: 100%
7 | Create and Revise Project Charter | Miguel, Evelyn | 100% | 2023-09-07 | 2023-09-10 | 3 | 5 | 2023-09-11 2023-09-11 M: 100%
8 | Meeting with Dr Rosser | All | 100% | 2023-09-12 | 2023-09-12 | 0.25 | 0.25 | 2023-09-11 2023-09-13 W: 100%
9 | Create and Revise Change Log | All | 100% | 2023-08-31 | 2023-09-21 | 1 | 1 | 2023-09-18 2023-09-22 F: 100%
10 | Create and Revise Meeting Communications | Miguel | 100% | 2023-08-31 | 2023-09-21 | 1 | 1 | 2023-09-18 2023-09-22 F: 100%
Milestone 2
11 | Meeting with GA | All | 100% | 2023-09-28 | 2023-09-28 | 0.25 | 0.25 | 2023-09-25 2023-09-29 F: 100%
12 | Create and Revise Project Scope Statement | Miguel, Evelyn | 100% | 2023-09-21 | 2023-09-30 | 3 | 4 | 2023-09-25 2023-10-01 S: 100%
13 | Create and Revise Work Breakdown Structure | Miguel, Evelyn, Michael | 100% | 2023-09-22 | 2023-09-30 | 2 | 3 | 2023-09-25 2023-10-01 S: 100%
14 | Create and Revise Statement of Work | Evelyn | 100% | 2023-09-25 | 2023-09-30 | 2 | 3 | 2023-09-25 2023-10-01 S: 100%
15 | Create and Revise Work Breakdown Structure Dictionary | Natalie, Evelyn | 100% | 2023-09-22 | 2023-10-05 | 4 | 4 | 2023-10-02 6 F: 100%
16 | Create and Revise Gantt Chart | Michael | 100% | 2023-09-25 | 2023-10-05 | 4 | 4 | 2023-10-02 6 F: 100%
17 | Meeting with Dr Rosser | All | 100% | 2023-10-05 | 2023-10-05 | 0.25 | 0.25 | 2023-10-02 6 F: 100%
18 | Create and Revise Economic Feasibility Analysis | Miguel | 100% | 2023-09-25 | 2023-10-08 | 2 | 3 | 2023-10-09 9 M: 100%
19 | Create and Revise Client and Control Documents | All | 100% | 2023-09-25 | 2023-10-14 | 2 | 2 | 2023-10-09 15 S: 100%
Milestone 3
20 | Create and Revise Baseline Project Plan | Miguel | 100% | 2023-10-15 | 2023-10-25 | 8 | 6 | 2023-10-23 26 T: 100%
21 | Meeting with GA | All | 100% | 2023-10-26 | 2023-10-26 | 0.25 | 0.25 | 2023-10-23 28 S: 100%
22 | Create and Revise Requirements Documentation | Michael | 100% | 2023-10-15 | 2023-10-30 | 2 | 2 | 2023-10-30 31 T: 100%
23 | Create and Revise Gantt Chart | Michael | 100% | 2023-10-15 | 2023-10-30 | 1 | 1 | 2023-10-30 31 T: 100%
24 | Meeting with Dr Rosser | All | 100% | 2023-11-02 | 2023-11-02 | 0.25 | 0.25 | 2023-10-30 3 F: 100%
25 | Create and Revise User Interface Wireframes | Evelyn | 100% | 2023-10-20 | 2023-11-05 | 3 | 3 | 2023-11-06 6 M: 100%
26 | Create and Revise Risk Management Plan | All | 100% | 2023-10-25 | 2023-11-08 | 3 | 4 | 2023-11-06 9 T: 100%
27 | Create and Revise Control Documents | All | 100% | 2023-11-01 | 2023-11-10 | 1 | 2 | 2023-11-06 11 S: 100%
Milestone 4
28 | Meeting with GA | All | 100% | 2023-11-17 | 2023-11-17 | 0.25 | 0.25 | 2023-11-13 18 S: 100%
29 | Create and Revise Context Diagram | Miguel | 100% | 2023-11-11 | 2023-11-22 | 4 | 0.75 | 2023-11-20 23 T: 100%
30 | Create and Revise Data Flow Diagram | Evelyn | 100% | 2023-11-11 | 2023-11-25 | 4 | 3 | 2023-11-20 26 S: 100%
31 | Create and Revise Use Case Diagram | Michael | 100% | 2023-11-20 | 2023-11-30 | 4 | 3 | 2023-11-27 1 F: 100%
32 | Meeting with Dr Rosser | All | 100% | 2023-11-30 | 2023-11-30 | 0.25 | 0.3 | 2023-11-27 1 F: 100%
33 | Create and Revise Presentation Slides | All | 100% | 2023-11-20 | 2023-12-04 | 3 | 3 | 2023-12-04 5 T: 100%
34 | Create and Revise Control Documents | All | 100% | 2023-11-30 | 2023-12-06 | 2 | 3 | 2023-12-04 7 T: 100%

## ISQA 4120
| G6 Maverick Analyzers | [7 empty] | ► Watch How to Make a Gantt Chart in Excel
| ISQA 4120 Gantt Chart |  | Project Start: | 2024-01-22
| Michael Mulvey, Evelyn Espinoza-Macias, |  | Today: | 2023-12-04 13:33
| Miguel Rocha, Natalie Moore |  | Display Week: | 1 |  |  |  | 2024-01-22 | [6 empty] | 2024-01-29 | [6 empty] | 2024-02-05 | [6 empty] | 2024-02-12 | [6 empty] | 2024-02-19 | [6 empty] | 2024-02-26 | [6 empty] | 2024-03-04 | [6 empty] | 2024-03-11 | [6 empty] | 2024-03-18 | [6 empty] | 2024-03-25 | [6 empty] | 2024-04-01 | [6 empty] | 2024-04-08 | [6 empty] | 2024-04-15 | [6 empty] | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13
|  |  |  | *LEAVE AS WEEK 1* |  |  |  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
ID | TASK | ASSIGNED TO | PROGRESS | START | END | Estimated Hours | ACTUAL HOURS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
[6 empty] | 207 | 0
Milestone 5
1 | Create and Revise Application Overview | Natalie | 0% | 2024-01-22 | 2024-01-28 | 4 | bar: 2024-01-22 22 M; 2024-01-29 29 M
2 | Create and Revise Use Case Diagrams | Evelyn | 0% | 2024-01-27 | 2024-02-01 | 3 | bar: 2024-01-22 27 S; 2024-01-29 2 F
3 | Create and Revise Data Model (ER Diagram) | Evelyn | 0% | 2024-02-01 | 2024-02-06 | 3 | bar: 2024-01-29 1 T; 2024-02-05 7 W
4 | Create and Revise Mockups | Miguel | 0% | 2024-02-06 | 2024-02-08 | 5 | bar: 2024-02-05 6 T; 2024-02-05 9 F
5 | Create and Revise Release Plan | Michael | 0% | 2024-02-08 | 2024-02-10 | 6 | bar: 2024-02-05 8 T; 2024-02-05 11 S
6 | Create and Revise Tasks Management Plan | All | 0% | 2024-02-08 | 2024-02-14 | 5 | bar: 2024-02-05 8 T; 2024-02-12 15 T
7 | Create and Revise Communications Management Plan | All | 0% | 2024-02-08 | 2024-02-14 | 2 | bar: 2024-02-05 8 T; 2024-02-12 15 T
8 | Create and Revise Gantt Chart | Michael | 0% | 2024-02-13 | 2024-02-16 | 4 | bar: 2024-02-12 13 T; 2024-02-12 17 S
9 | Create and Revise Contingency Plan | Miguel | 0% | 2024-02-15 | 2024-02-17 | 5 | bar: 2024-02-12 15 T; 2024-02-12 18 S
10 | Create and Revise Link to GitHub Repository | Natalie | 0% | 2024-02-17 | 2024-02-18 | 1 | bar: 2024-02-12 17 S; 2024-02-19 19 M
Milestone 6
11 | Create and Revise PyCharm Project | Michael | 0% | 2024-02-19 | 2024-02-25 | 3 | bar: 2024-02-19 19 M; 2024-02-26 26 M
12 | Create and Revise Front-End code | Miguel | 0% | 2024-02-24 | 2024-03-01 | 20 | bar: 2024-02-19 24 S; 2024-02-26 2 S
13 | Create and Revise Back-End code | Evelyn | 0% | 2024-02-29 | 2024-03-06 | 20 | bar: 2024-02-26 29 T; 2024-03-04 7 T
14 | Create and Revise Linking code to GitHub | Natalie | 0% | 2024-03-05 | 2024-03-06 | 1 | bar: 2024-03-04 5 T; 2024-03-04 7 T
15 | Create and Revise Data Model (ER Diagram) | Evelyn | 0% | 2024-03-03 | 2024-03-09 | 2 | bar: 2024-02-26 3 S; 2024-03-04 10 S
16 | Create and Revise Mockups | Miguel | 0% | 2024-03-07 | 2024-03-09 | 3 | bar: 2024-03-04 7 T; 2024-03-04 10 S
17 | Create and Revise Tasks Management Plan | All | 0% | 2024-03-09 | 2024-03-15 | 3 | bar: 2024-03-04 9 S; 2024-03-11 16 S
18 | Create and Revise Communications Management Plan | All | 0% | 2024-03-09 | 2024-03-15 | 2 | bar: 2024-03-04 9 S; 2024-03-11 16 S
19 | Create and Revise Gantt Chart | Michael | 0% | 2024-03-14 | 2024-03-17 | 2 | bar: 2024-03-11 14 T; 2024-03-18 18 M
Milestone 7
20 | Create and Revise Front-End code | Miguel | 0% | 2024-03-18 | 2024-03-24 | 20 | bar: 2024-03-18 18 M; 2024-03-25 25 M
21 | Create and Revise Back-End code | Evelyn | 0% | 2024-03-23 | 2024-03-30 | 20 | bar: 2024-03-18 23 S; 2024-03-25 31 S
22 | Create and Revise Linking code to GitHub | Natalie | 0% | 2024-03-29 | 2024-03-30 | 1 | bar: 2024-03-25 29 F; 2024-03-25 31 S
23 | Create and Revise Test Cases Documentation | Natalie | 0% | 2024-03-28 | 2024-04-04 | 5 | bar: 2024-03-25 28 T; 2024-04-01 5 F
24 | Create and Revise Presentation Design | Michael | 0% | 2024-04-02 | 2024-04-07 | 3 | bar: 2024-04-01 2 T; 2024-04-08 8 M
25 | Create and Revise Technical Manual | Miguel | 0% | 2024-04-05 | 2024-04-10 | 6 | bar: 2024-04-01 5 F; 2024-04-08 11 T
26 | Create and Revise Tasks Management Plan | All | 0% | 2024-04-08 | 2024-04-12 | 4 | bar: 2024-04-08 8 M; 2024-04-08 13 S
27 | Create and Revise Communications Management Plan | All | 0% | 2024-04-08 | 2024-04-12 | 2 | bar: 2024-04-08 8 M; 2024-04-08 13 S
28 | Create and Revise Gantt Chart | Michael | 0% | 2024-04-12 | 2024-04-14 | 2 | bar: 2024-04-08 12 F; 2024-04-15 15 M
Milestone 8
29 | Create and Revise Front-End code | Miguel | 0% | 2024-04-15 | 2024-04-22 | 20 | bar: 2024-04-15 15 M; 2024-04-22 23 T
30 | Create and Revise Back-End code | Evelyn | 0% | 2024-04-22 | 2024-04-29 | 20 | bar: 2024-04-22 22 M; 2024-04-29 30 T
31 | Create and Revise Linking code to GitHub | Natalie | 0% | 2024-04-29 | 2024-04-30 | 1 | bar: 2024-04-29 29 M; 2024-04-29 1 W
32 | Create and Revise Test Cases Documentation | Natalie | 0% | 2024-05-01 | 2024-05-09 | 4 | bar: 2024-04-29 1 W; 2024-05-06 10 F
33 | Create and Revise Presentation Slides | Michael | 0% | 2024-05-09 | 2024-05-14 | 3 | bar: 2024-05-06 9 T; 2024-05-13 15 W
34 | Create and Revise Data Model (ER Diagram) | Evelyn | 0% | 2024-05-15 | 2024-05-17 | 2 | [118 empty] | 0% | bar: 2024-05-13 15 W
| SIMPLE GANTT CHART by Vertex42.com |  |  |  | 2018-01-13
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [6 empty] | 2024-01-22 24 W: * =SPARKLINE(E9,{"charttype","bar";"max",100%;"color1","green";"empty","zero"})
© 2018-2019 Vertex42 LLC

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.